Many Voices Queensland Aboriginal and Torres Strait Islander Languages Policy Action Plan Traffic Light Report 2020–2022

# Table of Contents

[Many Voices Queensland Aboriginal and Torres Strait Islander Languages Policy Action Plan Traffic Light Report 2020–2022 2](#_Toc148093257)

[Table of Contents 2](#_Toc148093258)

[Traffic Light Report Many Voices: Queensland Aboriginal and Torres Strait Islander Languages Policy 3](#_Toc148093259)

[PRIORITY 01: PATHWAYS 4](#_Toc148093260)

[PRIORITY 02: ACTION AND ACTIVATION 6](#_Toc148093261)

[PRIORITY 03: RESTORATION AND TRANSMISSION 8](#_Toc148093262)

[PRIORITY 04: RECOGNITION AND PROMOTION 9](#_Toc148093263)

[PRIORITY 04: RECOGNITION AND PROMOTION 10](#_Toc148093264)

[PRIORITY 04: RECOGNITION AND PROMOTION 12](#_Toc148093265)

[Glossary of Acronyms 14](#_Toc148093266)

[Acknowledgement 15](#_Toc148093267)

# Traffic Light Report Many Voices: Queensland Aboriginal and Torres Strait Islander Languages Policy

The Queensland Government worked in partnership with Aboriginal and Torres Strait Islander language experts to co-design and develop the *Many Voices: Queensland Aboriginal and Torres Strait Islander Languages Policy* (the Languages Policy).

It delivers on the action in the *Queensland Government Reconciliation Action Plan 2018–2022* for a co-designed Aboriginal and Torres Strait Islander languages policy to be developed with the Aboriginal and Torres Strait Islander community.

The Languages Policy outlines four priority areas for government action to ensure that Aboriginal and Torres Strait Islander languages in Queensland are strong, acknowledged, maintained and accessible.

These include:

1. **PATHWAYS:** strategies aimed at developing physical, cultural and social infrastructure that provides strong foundations to support language growth and maintenance.
2. **ACTION AND ACTIVATION:** development of language resources and expertise to grow community capacity to share and encourage the use of Aboriginal and Torres Strait Islander languages across all Queensland communities.
3. **RESTORATION AND TRANSMISSION:** strategies to increase the number of people speaking Aboriginal and Torres Strait Islander languages regularly including information storage, expertise and local access to learning.
4. **RECOGNITION AND PROMOTION:** strategies to grow community awareness and understanding of Aboriginal and Torres Strait Islander languages to encourage reconciliation and pride in Queensland’s unique cultural heritage.

## About the Traffic Light Report

This Traffic Light Report provides an implementation update on the *Many Voices: Queensland Aboriginal and Torres Strait Islander Languages Policy Action Plan 2020–2022* and provides an update on the outcomes achieved under the four priority areas for government action, from 1 July 2020 to 30 June 2022.

## Legend

|  |  |
| --- | --- |
| Traffic Light | Description |
| Completed | Fully implemented, or now part of business as usual |
| On track | On track to be completed by due date |
| Minor delays or complications | Some issues or delays in delivery requiring close monitoring. The impact should not affect the overall success of the program when managed |
| Discontinued | Not implemented and ceased |

# PRIORITY 01: PATHWAYS

Pathways is about building the physical, cultural and social infrastructure foundations to support the growth and maintenance of Aboriginal languages and Torres Strait Islander languages in Queensland.

Building a solid foundation of support will enable future actions under the Action Plan to be progressed in future iterations of the Action Plan.

### July 2020 – June 2022

| Action | Responsibility | Status |
| --- | --- | --- |
| 1.1 Investigate the creation of training packages to support the professional development of Aboriginal and Torres Strait Islander language educators. | DoE | On track |
| 1.2 Pilot the delivery of certificate courses and professional development for Aboriginal and Torres Strait Islander language educators. | DoE | Minor delays or complications Procurement of a service provider to deliver the certificate courses  and professional development is in progress. |
| 1.3 Engage with local community groups to promote certification opportunities for Aboriginal and Torres Strait Islander peoples who are First Nations Language experts. | DSDSATSIP | Discontinued  Promotion of certification opportunities for language experts is not feasible for the agencies. |
| 1.4 Development of Family Led Decision-Making to increase the cultural authority of Aboriginal and Torres Strait Islander families and communities in the youth justice system with the following Aboriginal Community Controlled Organisations: Kurbingui, Wuchopperan, Goolburri and  the Aboriginal and Torres Strait Islander Community Health Service (ATSICHS). | DCYJMA | On track |
| 1.5 Support communities through the Stronger Places, Stronger People collective impact initiatives in Logan, Gladstone and Rockhampton to continue to address local issues, including cultural issues and cultural identity. | DCHDE | Discontinued  Stronger Places, Stronger People supports community-led responses to local issues, which may include cultural issues, however this depends on the interests and direction of local communities. |
| 1.6 Continue to create economic opportunities for Aboriginal and Torres Strait Islander artists through cultural expression such as the promotion of traditional language and story sharing through the Backing Indigenous Art initiative. | DCHDE (AQ) | On track |
| 1.7 Continue ongoing management of state-wide whole-of- government language services Standing Offer Arrangement including interpreting and translation of Aboriginal and Torres Strait Islander languages. | QH | On track |
| 1.8 Initiate, develop and establish Aboriginal and Torres Strait Islander language maintenance and revival through a range of activities across Queensland, through the Indigenous Languages Grants Program. | DoE DSDSATSIP | On track |

# PRIORITY 02: ACTION AND ACTIVATION

Action and activation focuses on sharing and encouraging the development of language expertise and resources to grow capacity.

Nurturing relationships, developing skills, building capacity, and influencing people, agencies, and organisations, to encourage the ongoing development and increased use of Aboriginal languages and Torres Strait Islander languages over time.

## July 2020 – June 2022

| Action | Responsibility | Status |
| --- | --- | --- |
| 2.1 Continue the employment and contracting of accredited Magistrate Court interpreters, such as the Wik Mungkan interpreters at the Aurukun Magistrates Court. | DJAG | Minor delays or complications  Based on availability of Wik interpreters. |
| 2.2 Continue to provide funding to the Aurukun Community Indigenous Corporation as part of the Aurukun Restorative Justice Program to Thaa' Pant to deliver peacekeeping and meditation services, including meditations conducted in Wik Mungkan language. | DJAG | On track |
| 2.3 Increase the use of Aboriginal and Torres Strait Islander Languages in and across all aspects of cultural tourism. | DTIS | On track |
| 2.4 Support the Murridhagun Cultural Centre to provide cultural support, including language speakers, and advice to Queensland Corrective Services staff to support the relationship Aboriginal and Torres Strait Islander prisoners have with their cultural identity. | QCS | On track |
| 2.5 Implement the Australian Curriculum Framework for Aboriginal Languages and Torres Strait Islander Languages in Queensland State Schools. | DoE | On track |
| 2.6 Optimise the translation of Bushfire Awareness and Preparedness materials into Aboriginal and Torres Strait Islander languages statewide. | QFES | Discontinued  Following preliminary project scope, it was determined not feasible to translate all Bushfire Awareness and Preparedness materials across the state due to high- cost, numerous languages versus low demand. |

# PRIORITY 03: RESTORATION AND TRANSMISSION

Restoration and transmission will focus on strategies that encourage an increase in the number of people regularly speaking Aboriginal languages and Torres Strait

Islander languages, including information storage, expertise and access to learning.

The outcome of this priority is to see an increased number of peoples speaking, sharing and storing Aboriginal languages and Torres Strait Islander languages, resulting in an easier transmission of languages in future.

## July 2020 – June 2022

| Action | Responsibility | Status |
| --- | --- | --- |
| 3.1 Explore the viability of small grant funding for artists to provide community- based art activities that promote Aboriginal and Torres Strait Islander languages. | DCHDE (AQ) DSDSATSIP | On track |
| 3.2 Provide community access to the recording facilities at the Bulmba-ja Arts Centre (Cairns) to preserve, maintain and promote Aboriginal and Torres Strait Islander languages. | DCHDE (AQ) | On track |
| 3.3 Embed active efforts to implement and give full effect to all five elements of the Aboriginal and Torres Strait Islander Child Placement Principle across the five system elements of the family support system (legislation, policy, programs, processes and practice). In particular, the Connection principle reinforces a child's right to be supported to develop and maintain a connection with the child's family, community, culture, traditions and  language, particularly when the child is in the care of a person who is not an Aboriginal or Torres Strait Islander person. | DCYJMA | On track |
| 3.4 Provide tools and professional development to public libraries and Indigenous Knowledge Centres so they can support communities to record and document languages. | DCHDE (SLQ) | On track |
| 3.5 Support Queensland State Schools and Aboriginal and Torres Strait Islander communities to work together to increase the growth of Aboriginal and Torres Strait Islander language through use in the classroom. | DoE | On track |
| 3.6 Provide guidance on the Copyright and Intellectual Property rights of Aboriginal and Torres Strait Islander language speakers to protect the cultural property created during the development of teaching materials in schools. | DoE | On track |

# PRIORITY 04: RECOGNITION AND PROMOTION

Recognition and promotion seeks to increase awareness and understanding of Aboriginal languages and Torres Strait Islander languages at a wider community level.

This will encourage reconciliation and pride in Queensland’s unique cultural heritage and embed Aboriginal languages and Torres Strait Islander languages as an integral part of Queensland’s future growth and development.

## July 2020 – June 2022

| Action | Responsibility | Status |
| --- | --- | --- |
| 4.1 Provide professional development opportunities for teachers to enable them to support Aboriginal and Torres Strait Islander students whose first language is a language or dialect other than English. | DoE | On track |
| 4.2 Explore strategies for the recognition and promotion of Aboriginal and Torres Strait Islander languages through place names. | DoR | Minor delays or complications  The minor delay is due to an administrative delay in signing the contract. |
| 4.3 Explore the impact of history on Aboriginal peoples’ and Torres Strait Islander peoples' languages as part of truth telling and healing and the Path to Treaty. | DSDSATSIP | On track |
| 4.4 Provide early childhood education and care services with information on including  Aboriginal and Torres Strait Islander languages in their early childhood programs, through capability development, newsletters and websites such as Foundation for Success. | DoE | On track |
| 4.5 Work in partnership across government to support and promote the value of recognising, reinvigorating and promoting Aboriginal  and Torres Strait Islander cultures, including traditional languages. | DSDSATSIP | Completed |
| 4.6 Ensure Aboriginal and Torres Strait Islander language is incorporated into work across the Queensland Government as part of Acknowledgement of Country. | DSDSATSIP | On track |

# PRIORITY 04: RECOGNITION AND PROMOTION

Recognition and promotion seeks to increase awareness and understanding of Aboriginal languages and Torres Strait Islander languages at a wider community level.

This will encourage reconciliation and pride in Queensland’s unique cultural heritage and embed Aboriginal languages and Torres Strait Islander languages as an integral part of Queensland’s future growth and development.

## July 2020 – June 2022

| Action | Responsibility | Status |
| --- | --- | --- |
| 4.7 Explore strategies to support all schools to recognise and acknowledge the Aboriginal and Torres Strait Islander Country and languages  of their school location on signage and school websites. | DoE | Minor delays or complications  A strategy to support schools to recognise and acknowledge the Aboriginal and Torres Strait Islander Country and languages of their school location on signage and school websites through a co-design process with local Aboriginal and Torres Strait Islander community members is yet to commence.  Initial scoping identified that due to the size and complexity of the action, an extended planning period is required to design a strategy that supports all schools to appropriately recognise and acknowledge the Aboriginal and Torres Strait Islander Countries and languages of their location on school signage and websites. |
| 4.8 Continue to use the 'Look to the Stars' artwork to encourage conversations, across all languages, and work towards reconciliation, understanding and respect. | QPS | On track |
| 4.9 Support and guide non-Indigenous organisations/operators to engage and promote traditional languages in a respectful way by linking with Traditional Owners and key Aboriginal and Torres Strait Islander language stakeholders. | DSDSATSIP | On track |
| 4.10 Develop a 'Culturally Respectful Language Guide' to inform preparation of the Department of the Premier and Cabinet's internal and external documents and communications. | DPC | Completed |

# PRIORITY 04: RECOGNITION AND PROMOTION

Recognition and promotion seeks to increase awareness and understanding of Aboriginal languages and Torres Strait Islander languages at a wider community level.

This will encourage reconciliation and pride in Queensland’s unique cultural heritage and embed Aboriginal languages and Torres Strait Islander languages as an integral part of Queensland’s future growth and development.

## July 2020 – June 2022

| Action | Responsibility | Status |
| --- | --- | --- |
| 4.11 Increase the naming of shared meeting spaces in 1 William Street using Aboriginal and Torres Strait Islander languages to grow awareness and understanding. | DPC DSDSATSIP | Minor delays or complications  Acknowledging the inherent connection between Aboriginal and Torres Strait Islander languages, and Country is imperative to ensuring the appropriate and authorised language is used for naming purposes. Identifying the First Nations parties in Brisbane with cultural authority is complex.  Department of the Premier and Cabinet and Department of Seniors, Disability Services and Aboriginal and Torres Strait Islander Partnerships will continue to engage with First Nations peoples in Brisbane to guide consultation on the naming of shared spaces in 1 William Street. |
| 4.12 Areas within Queensland Corrective Service facilities continue to acknowledge Traditional language through the naming of areas. | QCS | On track |
| 4.13 Increase the recognition of Aboriginal and Torres Strait Islander languages and build stronger relationships with First Nations peoples through the implementation of a National Parks First Nations Naming Project sprint. | DES | Completed  The original project was a sprint project that ended in December 2020 and reverted to business as usual.  All project outcomes and milestones were reported through the Department of Environment and Sciences Delivery Office. |
| 4.14 Encourage the revitalisation of language in alignment with the Gurra Gurra Framework 2020–2026 through appropriate and authorised use of language. | DES | On track |
| 4.15 Continue the use of Indigenous interpretive signage and physical activities across Queensland Recreation Centres to promote awareness and understanding of Aboriginal and Torres Strait Islander languages and culture. | DTIS | On track |
| 4.16 Increase the recognition of Aboriginal and Torres Strait Islander languages and build stronger relationships with First Nations peoples through the implementation of the Department of Transport and Main Road's Naming of Infrastructure Policy. | DTMR | On track |

# Glossary of Acronyms

|  |  |
| --- | --- |
| Department | Abbreviation |
| Department of Communities, Housing and Digital Economy | DCHDE |
| Arts Queensland | AQ |
| State Library of Queensland | SLQ |
| Queensland State Archives | QSA |
| Department of Children, Youth Justice and Multicultural Affairs | DCYJMA |
| Department of Environment and Science | DES |
| Department of Justice and Attorney-General | DJAG |
| Department of Education | DoE |
| Department of the Premier and Cabinet | DPC |
| Department of Resources | DoR |
| Department of Seniors, Disability Services and Aboriginal and Torres Strait Islander Partnerships | DSDSATSIP |
| Department of Tourism, Innovation and Sport | DTIS |
| Department of Transport and Main Roads | DTMR |
| Queensland Corrective Services | QCS |
| Queensland Fire and Emergency Services | QFES |
| Queensland Health | QH |
| Queensland Police Service | QPS |

# Acknowledgement

We pay our respects to the Aboriginal and Torres Strait Islander ancestors of this land, their spirits and their legacy. The foundations laid by these ancestors—our First Australians—give strength, inspiration and courage to current and future generations, both Indigenous and non- Indigenous, towards creating a better Queensland.

We recognise it is our collective efforts and responsibility as individuals, communities and governments to ensure equality, recognition and advancement of Aboriginal and Torres Strait Islander Queenslanders across all aspects of society and everyday life.

On behalf of the Queensland Government, we offer a genuine commitment to fearlessly represent, advocate for and promote the needs of Aboriginal and Torres Strait Islander Queenslanders with unwavering determination, passion and persistence.

As we reflect on the past and give hope for the future, we walk together on our shared journey to reconciliation where all Queenslanders are equal.

## Copyright

Copyright © State of Queensland, July 2021. Copyright protects this publication. Excerpts may be reproduced with acknowledgment of the State of Queensland.

This document is licensed by the State of Queensland under a Creative Attribution (CC BY) 3.0 Australian license.

CC BY License Summary Statement: In essence, you are free to copy, communicate and adapt the Many Voices: Queensland Aboriginal and Torres Strait Islander Languages Policy Action Plan as long as you attribute the work to the State of Queensland. To view a copy of this license, visit: [www.creativecommons.org/ licenses/by/3.0/au/deed.en](http://www.creativecommons.org/%20licenses/by/3.0/au/deed.en).

While every care has been taken in preparing this publication, the State of Queensland accepts no responsibility for decisions or actions taken as a result of any data, information, statement or advice, expressed or implied, contained within. To the best of our knowledge, the content was correct at the time of publishing.

The information in this publication is general and does not take into account individual circumstances or situations.

[www.qld.gov.au/**many-voices**](http://www.qld.gov.au/many-voices)